## Activities (hidden)
Activities
NO. | Activities | Description | Total Date
1 | Documentation and planning
| Requirement Gathering & System Planning | Conduct interviews and meetings with users to gather and analyze system requirements. | 9
| Diagram & Flow Design | Create and review system flow diagrams to support clear and accurate development. | 12
| Technical Spec + Timeline Finalization | Specify system architecture and confirm project timeline and milestones. | 9
2 | Development and Integration
Frontend Development
| UX/UI wireframe design | Create and validate wireframes to guide user interface design and development. | 10
| Main Page + Menu Navigation | Design main page and menu navigation to ensure clear and user-friendly system access. | 7
| Login / Register Page | Create and validate secure login and registration interfaces. | 8
| Charger Page | Create and validate secure login and registration interfaces. | 6
| MDB Iot Page | Create and validate MDB IoT page for device monitoring and control. | 7
| Maintenance report page | Create and validate maintenance report page for effective recording and tracking of maintenance tasks. | 7
| Test report page | Create and validate test report page for efficient test result management. | 11
| Predictive Maintenance page | Create and validate predictive maintenance page for monitoring and forecasting maintenance tasks. | 9
| Health Index Page | Create and validate health index page for clear monitoring of system health. | 8
| Setting Page | Create and validate setting page for user configuration and security. | 7
Backend API + DB Integration (12.2.1)
| Create Data Base | Design and build database with optimized structure and tested integrity. | 2
| Connect MongoDB/PostgreSQL | Connect and validate database access for MongoDB/PostgreSQL with CRUD operations. | 4
| Auth API | Create and test secure Auth API for user login and access control. | 6
| Station Info API | Create and test Station Info API for efficient station data access. | 13
| Setup MQTT/WS for real-time | Setup and validate MQTT/WebSocket for reliable real-time data exchange. | 6
Predictive AI Module Integration (12.2.3)
| File Upload/Download | Implement and manage secure file upload and download functionality. | 7
| Upload/Download system of Test & PM Report | Create and validate upload/download system for Test & PM reports with secure file handling. | 7
| Setup REST API for 7 AI Modules | Create and test REST APIs for 7 AI modules with secure and scalable design. | 11
| Design Prediction Input/Output UI | Create and validate prediction input/output UI for effective user interaction. | 9
| Telegram/Email Notification Setting | Create and test Telegram and Email notification settings with user customization. | 15
Final Test
| Connect API , End to End test , Debug & Optimize | Connect APIs, conduct E2E testing, debug issues, and optimize system performance. | 11
3 | System Testing, UI Refinement, and Deployment
| Internal Testing (Unit & Integration) | Conduct unit and integration tests to ensure system quality and correctness. | 21
| System QA & Error Handling | Perform system QA and implement robust error handling for stability and usability. | 20
| Data Simulation & User Scenario Testing | Using simulated data and real-world scenarios to test system functionality and user experience before deployment. | 21
| User Training & User Manual & Documentation | Training and documentation to help users effectively operate the system. | 15
| UAT | The final testing phase where users verify the system meets their requirements before official release. | 21
| Feedback | Information or opinions given to improve performance, quality, or processes. | 10
| System Handover & Final Delivery | Final transfer of the completed system to the client with all deliverables for acceptance. | 12

## ชีต2 (hidden)
|  | Jul |  |  |  |  | Aug |  |  |  |  | Sep |  |  |  |  | Oct |  |  |  |  | Nov |  |  |  |  | Dec |  |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1
1 | Documentation and planning
| Requirement Gathering & System Planning | [40 empty] | WK | bar: Jul 2
| Diagram & Flow Design | [40 empty] | WK | bar: Jul 3
| Technical Spec + Timeline Finalization | [40 empty] | WK | bar: Jul 5 to Aug 1
2 | Development and Integration | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
Frontend Development | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| UX/UI wireframe design | [40 empty] | TD | bar: Aug 2
| Main Page + Menu Navigation | [40 empty] | WK | bar: Aug 4
| Login / Register Page | [40 empty] | TD | bar: Aug 5
| Charger Page | [40 empty] | WK | bar: Sep 1
| MDB Iot Page | [40 empty] | TD , WK | bar: Sep 2
| Maintenance report page | [40 empty] | TD | bar: Sep 3
| Test report page | [40 empty] | TD | bar: Sep 4; Oct 1
| Predictive Maintenance page | [40 empty] | TD | bar: Oct 1
| Health Index Page | [40 empty] | TD | bar: Oct 3
| Setting Page | [40 empty] | TD | bar: Oct 4
Backend API + DB Integration (12.2.1) | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Create Data Base | [40 empty] | TS | bar: Aug 2
| Connect PostgreSQL | [40 empty] | TS | bar: Aug 2
| Auth API | [40 empty] | TS | bar: Aug 3
| Station Info API | [40 empty] | TS , WK | bar: Aug 4
| Setup MQTT/WS for real-time | [40 empty] | TS , WK | bar: Sep 1
Predictive AI Module Integration (12.2.3) | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| File Upload/Download | [40 empty] | TS | bar: Sep 2
| Upload/Download system of Test & PM Report | [40 empty] | TS | bar: Sep 3
| Setup REST API for 7 AI Modules | [40 empty] | VA | bar: Sep 4; Oct 1
| Design Prediction Input/Output UI | [40 empty] | VA | bar: Oct 1
| Telegram/Email Notification Setting | [40 empty] | TS | bar: Oct 3
Final Test | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Connect API , End to End test , Debug & Optimize | [40 empty] | ALL | bar: Oct 5 to Nov 1
3 | System Testing, UI Refinement, and Deployment | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Internal Testing (Unit & Integration) | [40 empty] | ALL | bar: Nov 2
| System QA & Error Handling | [40 empty] | ALL | bar: Nov 5 to Dec 1
| Data Simulation & User Scenario Testing | [40 empty] | TS , TD | bar: Dec 3; Jan 1
| User Training & User Manual & Documentation | [40 empty] | ALL | bar: Jan 2
| UAT | [40 empty] | ALL | bar: Jan 4; Feb 1
| Feedback | [40 empty] | ALL | bar: Feb 2
| System Handover & Final Delivery | [40 empty] | ALL | bar: Feb 4 to Mar 1

## Confirmation
Requirements Confirmation Matrix
No | Item | Description | Clause | Check | Remarks
1 | Project Timeline | Presents the sequence and duration of project activities to facilitate effective planning and progress monitoring. | 12.1.1
2 | Project Resources | Resources required for project execution, including personnel, budget, equipment, and tools, to ensure project objectives are achieved. | 12.1.1
3 | Activities | Tasks or steps carried out within the project to achieve the planned objectives. | 12.1.1
4 | User Training Plan | A training plan designed to equip users with the knowledge and skills necessary to use the system or project effectively and correctly. | 12.1.1
5 | System Testing Plan | A plan for testing the system to ensure it functions correctly as specified and is ready for deployment. | 12.1.1
6 | Architecture design diagram | A diagram illustrating the system’s structure, showing key components, their interactions, and how they work together. | 12.1.2
7 | Use case diagram | A diagram that illustrates the system’s functionality by showing users (actors) and the main activities (use cases) the system supports. | 12.1.2
8 | Activity Diagram | A diagram that illustrates the sequence of workflows or activities in a process, from start to finish. | 12.1.2
9 | Entity Relationship Diagram (ERD) | A diagram that shows the relationships between entities in a system, used to design a structured and logical database. | 12.1.2