## Activities (hidden)
Activities
NO. | Activities | Description | Total Date
1 | Documentation and planning
| Requirement Gathering & System Planning | Conduct interviews and meetings with users to gather and analyze system requirements. | 9
| Diagram & Flow Design | Create and review system flow diagrams to support clear and accurate development. | 12
| Technical Spec + Timeline Finalization | Specify system architecture and confirm project timeline and milestones. | 9
2 | Development and Integration
Frontend Development
| UX/UI wireframe design | Create and validate wireframes to guide user interface design and development. | 10
| Main Page + Menu Navigation | Design main page and menu navigation to ensure clear and user-friendly system access. | 7
| Login / Register Page | Create and validate secure login and registration interfaces. | 8
| Charger Page | Create and validate secure login and registration interfaces. | 6
| MDB Iot Page | Create and validate MDB IoT page for device monitoring and control. | 7
| Maintenance report page | Create and validate maintenance report page for effective recording and tracking of maintenance tasks. | 7
| Test report page | Create and validate test report page for efficient test result management. | 11
| Predictive Maintenance page | Create and validate predictive maintenance page for monitoring and forecasting maintenance tasks. | 9
| Health Index Page | Create and validate health index page for clear monitoring of system health. | 8
| Setting Page | Create and validate setting page for user configuration and security. | 7
Backend API + DB Integration (12.2.1)
| Create Data Base | Design and build database with optimized structure and tested integrity. | 2
| Connect MongoDB/PostgreSQL | Connect and validate database access for MongoDB/PostgreSQL with CRUD operations. | 4
| Auth API | Create and test secure Auth API for user login and access control. | 6
| Station Info API | Create and test Station Info API for efficient station data access. | 13
| Setup MQTT/WS for real-time | Setup and validate MQTT/WebSocket for reliable real-time data exchange. | 6
Predictive AI Module Integration (12.2.3)
| File Upload/Download | Implement and manage secure file upload and download functionality. | 7
| Upload/Download system of Test & PM Report | Create and validate upload/download system for Test & PM reports with secure file handling. | 7
| Setup REST API for 7 AI Modules | Create and test REST APIs for 7 AI modules with secure and scalable design. | 11
| Design Prediction Input/Output UI | Create and validate prediction input/output UI for effective user interaction. | 9
| Telegram/Email Notification Setting | Create and test Telegram and Email notification settings with user customization. | 15
Final Test
| Connect API , End to End test , Debug & Optimize | Connect APIs, conduct E2E testing, debug issues, and optimize system performance. | 11
3 | System Testing, UI Refinement, and Deployment
| Internal Testing (Unit & Integration) | Conduct unit and integration tests to ensure system quality and correctness. | 21
| System QA & Error Handling | Perform system QA and implement robust error handling for stability and usability. | 20
| Data Simulation & User Scenario Testing | Using simulated data and real-world scenarios to test system functionality and user experience before deployment. | 21
| User Training & User Manual & Documentation | Training and documentation to help users effectively operate the system. | 15
| UAT | The final testing phase where users verify the system meets their requirements before official release. | 21
| Feedback | Information or opinions given to improve performance, quality, or processes. | 10
| System Handover & Final Delivery | Final transfer of the completed system to the client with all deliverables for acceptance. | 12

## Timeline (hidden)
|  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1
1 | Documentation and planning
| Requirement Gathering & System Planning | [36 empty] | WK | bar: Jul 2
| Diagram & Flow Design | [36 empty] | WK | bar: Jul 3
| Technical Spec + Timeline Finalization | [36 empty] | WK | bar: Jul 5 to Aug 1
2 | Development and Integration | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
Frontend Development | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| UX/UI wireframe design | [36 empty] | TD | bar: Aug 1
| Main Page + Menu Navigation | [36 empty] | WK | bar: Aug 3
| Login / Register Page | [36 empty] | TD | bar: Aug 4
| Charger Page | [36 empty] | WK | bar: Sep 1
| MDB Iot Page | [36 empty] | TD , WK | bar: Sep 2
| Maintenance report page | [36 empty] | TD | bar: Sep 3
| Test report page | [36 empty] | TD | bar: Sep 4
| Predictive Maintenance page | [36 empty] | TD | bar: Oct 1
| Health Index Page | [36 empty] | TD | bar: Oct 2
| Setting Page | [36 empty] | TD | bar: Oct 3
Backend API + DB Integration (12.2.1) | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Create Data Base | [36 empty] | TS | bar: Aug 1
| Connect MongoDB | [36 empty] | TS | bar: Aug 1
| Auth API | [36 empty] | TS | bar: Aug 2
| Station Info API | [36 empty] | TS , WK | bar: Aug 3 to Aug 4
| Setup MQTT/WS for real-time | [36 empty] | TS , WK | bar: Sep 1
Predictive AI Module Integration (12.2.3) | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| File Upload/Download | [36 empty] | TS | bar: Sep 2
| Upload/Download system of Test & PM Report | [36 empty] | TS | bar: Sep 3
| Setup REST API for 7 AI Modules | [36 empty] | VA | bar: Sep 4
| Design Prediction Input/Output UI | [36 empty] | VA | bar: Oct 1
| Telegram/Email Notification Setting | [36 empty] | TS | bar: Oct 2
Final Test | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Connect API , End to End test , Debug & Optimize | [36 empty] | ALL | bar: Oct 4 to Nov 1
3 | System Testing, UI Refinement, and Deployment | bar: Jul 1; Aug 1; Sep 1; Oct 1; Nov 1; Dec 1; Jan 1; Feb 1; Mar 1
| Internal Testing (Unit & Integration) | [36 empty] | ALL | bar: Nov 1
| System QA & Error Handling | [36 empty] | ALL | bar: Nov 4 to Dec 1
| Data Simulation & User Scenario Testing | [36 empty] | TS , TD | bar: Dec 3
| User Training & User Manual & Documentation | [36 empty] | ALL | bar: Jan 1
| UAT | [36 empty] | ALL | bar: Jan 3 to Feb 1
| Feedback | [36 empty] | ALL | bar: Feb 2
| System Handover & Final Delivery | [36 empty] | ALL | bar: Feb 4 to Mar 1

## Confirmation (hidden)
Requirements Confirmation Matrix
No | Item | Description | Clause | Check | Remarks
1 | Project Timeline | Presents the sequence and duration of project activities to facilitate effective planning and progress monitoring. | 12.1.1
2 | Project Resources | Resources required for project execution, including personnel, budget, equipment, and tools, to ensure project objectives are achieved. | 12.1.1
3 | Activities | Tasks or steps carried out within the project to achieve the planned objectives. | 12.1.1
4 | User Training Plan | A training plan designed to equip users with the knowledge and skills necessary to use the system or project effectively and correctly. | 12.1.1
5 | System Testing Plan | A plan for testing the system to ensure it functions correctly as specified and is ready for deployment. | 12.1.1
6 | Architecture design diagram | A diagram illustrating the system’s structure, showing key components, their interactions, and how they work together. | 12.1.2
7 | Use case diagram | A diagram that illustrates the system’s functionality by showing users (actors) and the main activities (use cases) the system supports. | 12.1.2
8 | Activity Diagram | A diagram that illustrates the sequence of workflows or activities in a process, from start to finish. | 12.1.2
9 | Entity Relationship Diagram (ERD) | A diagram that shows the relationships between entities in a system, used to design a structured and logical database. | 12.1.2

## สำเนาของ Confirmation (hidden)
Requirements Confirmation Matrix
No | Item | Description | Clause | Phase |  | Check | Remarks
1 | Project Timeline | Presents the sequence and duration of project activities to facilitate effective planning and progress monitoring. | 12.1.1 | 1
2 | Project Resources | Resources required for project execution, including personnel, budget, equipment, and tools, to ensure project objectives are achieved. | 12.1.1 | 1
3 | Activities | Tasks or steps carried out within the project to achieve the planned objectives. | 12.1.1 | 1
4 | User Training Plan | A training plan designed to equip users with the knowledge and skills necessary to use the system or project effectively and correctly. | 12.1.1 | 1
5 | System Testing Plan | A plan for testing the system to ensure it functions correctly as specified and is ready for deployment. | 12.1.1 | 1
6 | Architecture design diagram | A diagram illustrating the system’s structure, showing key components, their interactions, and how they work together. | 12.1.2 | 1
7 | Use case diagram | A diagram that illustrates the system’s functionality by showing users (actors) and the main activities (use cases) the system supports. | 12.1.2 | 1 | 4.3.1
8 | Activity Diagram | A diagram that illustrates the sequence of workflows or activities in a process, from start to finish. | 12.1.2 | 1 | 4.3.3
9 | Entity Relationship Diagram (ERD) | A diagram that shows the relationships between entities in a system, used to design a structured and logical database. | 12.1.2 | 1 | 4.2.3

## Test case
Project : | Intelligent Maintenance Platform as a Service
Document: | UAT Test Case
Purpose: | UAT test case to verify work meets TOR requirements.
Phase : | 1:Documentation and planning
TOR | Module | Requirement | Test ID | Tested By | Date
1.1 ระบบฐานข้อมูลแบบเรียลไทม์ (Page 11) | Database | Realtime Database เก็บข้อมูล Charger และ MDB ไม่ใช้วิธีการ refresh | UT001
1.2 ระบบฐานข้อมูลประวัติ (Page 11) | Database | Historical Database เก็บข้อมูล Charger และ MDB Station | UT002
1.3 ระบบฐานข้อมูลลูกค้า (Page 11) | Database | Customer Database | UT003
1.4 ระบบฐานข้อมูลเอกสาร (Page 11) | Database | Document CM/PM Report สามารถถูกเก็บเข้า Database | UT004
1.5 ระบบฐานข้อมูล Test Database (Page 11) | Database | Test Report สามารถถูกเก็บเข้า Database | UT005
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module MBD Dust Filters Prediction | UT006
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module Charger Dust Filters Prediction | UT007
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module Predictive Model To Analyze The Causes Of Charger Offline | UT008
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module Predictive Model For Abnormal Power Supply Of DC Charger | UT009
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module Network Problem Prediction System | UT010
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module The Remaining Useful Life (RUL) Prediction System For Equipment Inside A DC Charger | UT011
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module The System Analyzes The Problem Of The Charger Not Being Able To Supply Electricity | UT012
1.6 ระบบฐานข้อมูลซ่อมบำรุงเครื่องอัดประจุไฟฟ้าแบบคาดการณ์ Prediction Maintenance (Page 11) | Database | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module Health Index | UT013
2.1 ระบบบเชื่อมโยงข้อมูล iMPS กับ Charger (Page 11) | API | เชื่อมโยงข้อมูล iMPS Platfrom กับ Charger Manufacturer ผ่านโปรโตคอล MQTT | UT014
2.2 ระบบเชื่อมโยงข้อมูล iMPS BOX (Page 11) | API | เชื่อมโยงข้อมูล iMPS Platfrom กับ IMPS Box (ติดตั้งที่ตู้ CCB) จำนวน 10 สถานี เพื่อดึงข้อมูล Environment | UT015
2.4 ระบบ Notification (Page 11) | API | ระบบ Notification ผ่านทาง Telegram Notify | UT016
2.5 ระบบเชื่อมโยงข้อมูล iMPS กับ Customer (Page 11) | API | ระบบเชื่อมโยงข้อมูล iMPS Platfrom กับ Customer Database | UT017
2.7 ระบบเชื่อมโยงข้อมูล Test Report (Page 11) | API | Test Report | UT018
2.8 ระบบเชื่อมโยงข้อมูลประมวลผล Pedictive Maintenance (Page 11) | API | ข้อมูลสามารถส่งเพื่อเป็น input ให้ AI Module (ซ้ำกับ UT 8-13) | UT019
3.1 Main Page (Page 11) | Main Page | เทส Design และปุ่มกดต่างๆบนหน้า MainPage | UT020
3.1.1 Tab Menu (Page 12) | Main Page | Tab Menu (Home,About,Login,Register,Contact,Package,Customer) | UT021
3.1.2 Register (Page 12) | Register | register owner | UT022
3.1.2 Register (Page 12) | Register | register admin | UT023
3.1.3 Login (Page 12) | Login | able to login with Owner role | UT024
3.1.3 Login (Page 12) | Login | able to login with Admin role | UT025
3.1.3 Login (Page 12) | Login | able to login with Technician role | UT026
3.1.4 ข่าวสาร หรือ Package ต่าง ๆ (page 12) | Main Page | ส่วนแสดงข้อมูลข่าวสารของ iMPS Platfrom ใช้แสดงข้อมูลข่าวสารหรือ package ต่าง ๆ | UT027
3.2 My Charging Station Page (Page 12) | Dashboard | Oveview ของสถานีอัดประจุไฟฟ้า | UT028
3.2.1 Health Index (Page 12) | Dashboard | Health Index แสดงค่าสุขภาพของสถานี | UT029
3.2.2 Artificial Intelligence (Page 12) | Dashboard | Artificial Intelligence(Enable/Deactivate) การทำงานของ AI | UT030
3.2.3 PM/CM | Dashboard | รายละเอียดเกี่ยวกับการทำ PM/CM | UT031
3.2.4 Condition-Based Maintenance (CBM) (Page 12) | Dashboard | ควบคุมการเปิดใช้งาน CBM,chat GPT | UT032
3.2.5 Station View (Page 13) | Dashboard | ส่วนแสดง สถานะการ online/offline ของสถานี, รูปสถานี, เครื่องอัดประจุไฟฟ้า, ตู้สวิตช์ประธาน และ อุปกรณ์ภายในสถานี | UT033
3.2.6 Select Station (Page 13) | Dashboard | ค้นหาสถานีที่อยู่ภายใต้ Account นี้ | UT034
3.2.8 Tab Menu (Page 13) | Dashboard | Device, Setting, PM Report, Test Report,Monitor, MDB/CCB ,AI Module, My Profile, Settings, Sign Out, และ Help | UT035
3.3 Main Distribution Board (MDB) Cabinet (Page 14) (3.2.8.6 MDB/CCB (Page 13)) | MDB Page | Monitoring Main Distribution Board (MDB) | UT036
3.4 Device Page (Page 15) (3.2.8.1 Device (Page 13)) | Device Page | แสดงสถานะการทำงานของอุปกรณ์แต่ละตัวภายในเครื่องอัดประจุไฟฟ้า โดยจะแสดงจำนวนครั้งที่อุปกรณ์ทำงานและระยะเวลาที่อุปกรณ์ทำงาน | UT037
3.5 Setting Page (Page 16) (3.2.8.2 Setting (Page 13)) | Setting Page | ตั้งค่าสถานะเครื่องอัดประจุไฟฟ้า | UT038
3.6 PM Report (Page 17) (3.2.8.3 PM Report (Page 13)) | PM Report Page | ตั้งค่าสถานะเครื่องอัดประจุไฟฟ้า | UT039
3.7 Testing Report (Page 18) (3.2.8.4 Test Report (Page 13)) | Test Report Page | แสดงรายละเอียดเกี่ยวกับการทดสอบเครื่องอัดประจุไฟฟ้าด้วยเครื่องทดสอบ 5.2 upload file (Page 26) 5.4 export file (Page 26) | UT040
3.8 Monitor (CBM) Page (Page 19) (3.2.8.5 Monitor (CBM) (Page 13)) | Monitor (CBM) Page | ส่วนควบคุมการเปิดใช้งาน CBM, Chat GPT | UT041
3.9 AI Module Page (Page 21) | AI | 3.9.1 ระบบคาดการณ์การตันของฟิลเตอร์ของตู้สวิทช์ประธาน (MDB Dust Filters Prediction) (Page 21) | UT042
3.9 AI Module Page (Page 21) | AI | 3.9.2 ระบบคาดการณ์การตันของฟิลเตอร์ของเครื่องอัดประจุไฟฟ้า (Charger Dust Filters Prediction) (Page 21) | UT043
3.9 AI Module Page (Page 21) | AI | 3.9.3 ระบบคาดการณ์สาเหตุของการออฟไลน์ของเครื่องอัดประจุไฟฟ้า (Predictive Model To Analyze The Causes Of Charger Offline (Page 22) | UT044
3.9 AI Module Page (Page 21) | AI | 3.9.4 ระบบคาดการณ์สาเหตุการจ่ายไฟฟ้าผิดปกติของเครื่องอัดประจุไฟฟ้า (Predictive Model For Abnormal Power Supply Of DC Charger (Page 22) | UT045
3.9 AI Module Page (Page 21) | AI | 3.9.5 ระบบคาดการณ์สาเหตุของปัญหาเครือข่ายอินเตอร์เน็ต (Network Problem Prediction System) (Page 23) | UT046
3.9 AI Module Page (Page 21) | AI | 3.9.6 ระบบคาดการณ์อายุที่เหลืออยู่ของอุปกรณ์ภายในเครื่องอัดประจุไฟฟ้ากระแสตรง (The Remaning Useful Life(RUL) Prediction System For Equipment Inside a DC Charger) (Page 23) | UT047
3.9 AI Module Page (Page 21) | AI | 3.9.7 ระบบวิเคราะห์ปัญหาเครื่องอัดประจุไฟฟ้าไม่สามารถจ่ายไฟฟ้าได้ (The System Analyzes The Problem Of The Charger Not Being Able To Supply Electricity) (Page 24) | UT048
3.2.8.7 My Profile (Page 13) | Dashboard | Account Detail | UT049
3.2.8.8 Settings (Page 13) | Dashboard | Setting My Profile Detail | UT050
3.2.8.9 Sign Out (Page 13) | Dashboard | Log out | UT051
3.2.8.10 Help (Page 13) | Dashboard | คู่มือการใช้งาน | UT052
4.1.1 Add Charger (Page 26) | Dashboard | Add Charger (New Brand) | UT053
4.1.2 Add Charger (Page 26) | Dashboard | Add Charger (Same Brand) | UT054
4.1.3 Add setting value (Page 26) | Setting Page | Add setting value/Monitoring value | UT055
4.2.1 Add MDB IOT (Page 26) | MDB Page | เพิ่มค่าจาก MDB IOT ของ SITE ใหม่ได้ | UT056
4.2.6 Telegram Notification (Page 26) | Notification | ปรับตั้งค่า Telegram Notification เชื่อมโยงผ่าน User Account ได้ | UT057