## Gantt Chart_PhaseII
START DATE |  |  | 2025-07-08
% COMPLETED |  |  | #DIV/0! | [7 empty] | 2025-07-08 | [30 empty] | 2025-08-08 | [27 empty] | 2025-09-05 | [30 empty] | 2025-10-08 | [29 empty] | 2025-11-08 | [30 empty] | 2025-12-06 | [29 empty] | 2026-01-06 | [30 empty] | 2026-02-05 | [30 empty] | 2026-03-08 | [29 empty] | 2026-04-07 | [30 empty] | 2026-05-08 | [29 empty] | 2026-06-08
% PLANNED |  |  | 74%
[11 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
NO. | TASK TITLE | Phase | START DATE | DUE DATE |  | STATUS | PROGRESS% | PLANNED% | MILESTONE | MILESTONE DATE | time axis 2025-07-08 to 2026-07-07
1 | Documentation and planning | [6 empty] | 100%
| Requirement Gathering & System Planning |  | 2025-07-08 | 2025-07-14 | C |  |  | 100%
| UI/UX Wireframe Design |  | 2025-07-15 | 2025-07-21 | C |  |  | 100%
| Diagram & Flow Design |  | 2025-07-22 | 2025-07-26 | C |  |  | 100%
| Technical Spec + Timeline Finalization |  | 2025-07-27 | 2025-08-07 | C |  |  | 100%
2 | Development and Integration | [6 empty] | 100%
| Frontend Development |  | 2025-08-08 | 2025-09-20 |  |  |  | 100%
| Login/Register Page |  |  |  | C,3 |  |  | 100%
| Main Page + Menu Navigation |  |  |  | C |  |  | 100%
| My Charging Station UI |  |  |  | C |  |  | 100%
| Station Status, Device Info, Settings Page |  |  |  | C |  |  | 100%
| Backend API + DB Integration (12.2.1) |  | 2025-09-21 | 2025-10-10 |  |  |  | 100%
| Auth API, Station Info API |  |  |  | 3
| Connect MongoDB/PostgreSQL |  |  |  | 2 |  |  | 100%
| Setup MQTT/WS for real-time |  |  |  | 2 |  |  | 100%
| Predictive AI Module Integration (12.2.3) |  | 2025-10-11 | 2025-10-24 |  |  |  | 100%
| Setup REST API for 7 AI Modules |  |  |  | all |  |  | 100%
| Design Prediction Input/Output UI |  |  |  | 3 |  |  | 100%
| File Upload/Download + Notification System |  | 2025-10-25 | 2025-11-05 | 3 |  |  | 100%
| Upload/Download system of Test & PM Report |  |  |  | 3 |  |  | 100%
| LINE/Email Notification Setting UI |  |  |  | 2, |  |  | 100%
3 | System Testing, UI Refinement, and Deployment | [6 empty] | 100%
| Internal Testing (Unit & Integration) |  | 2025-11-06 | 2025-11-20 | all |  |  | 100%
| UI Polish & Responsive Design |  | 2025-11-21 | 2025-12-15 | C |  |  | 100%
| System QA & Error Handling |  | 2025-12-16 | 2026-01-05 | C, |  |  | 100%
| Data Simulation & User Scenario Testing |  | 2026-01-06 | 2026-03-05 | all |  |  | 100%
| User Manual & Documentation |  | 2026-03-06 | 2026-03-15 | 3,2 |  |  | 100%
| User Training & Feedback |  | 2026-03-16 | 2026-03-25 | C, |  |  | 100%
| System Handover & Final Delivery |  | 2026-03-26 | 2026-03-31 | all |  |  | 100%
100%
100%
100%
100%
100%
100%
40%
100%
100%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Sheet1
START DATE |  |  | 2025-07-08
% COMPLETED |  |  | #DIV/0! | [7 empty] | 2025-07-08 | [30 empty] | 2025-08-01 | [30 empty] | 2025-09-01 | [29 empty] | 2025-10-01 | [30 empty] | 2025-11-01 | [29 empty] | 2025-12-01 | [30 empty] | 2026-01-01 | [30 empty] | Febuary 2026 | [27 empty] | 2026-03-01
% PLANNED |  |  | #DIV/0!
[11 empty] | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
NO. | TASK TITLE | Phase | START DATE | DUE DATE | Resource | STATUS | PROGRESS% | PLANNED% | MILESTONE | MILESTONE DATE | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30
1 | Documentation and planning | bar: T to F; M to W; F; M to F; T to F; T to F; M to F; M; W to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; T to F; M to W; F; M to F; M to F; M to F; M to F; M to F; M to T; M to F; M to F; M to F; M to T; T to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to T
| Requirement Gathering & System Planning |  | 2025-07-08 | 2025-07-16 | WK | bar: T to W; F; M to W
| Diagram & Flow Design |  | 2025-07-17 | 2025-07-28 | WK | bar: T to F; T to F
| Technical Spec + Timeline Finalization |  | 2025-07-29 | 2025-08-06 | WK | bar: T to F; M to W
2 | Development and Integration | bar: T to F
Frontend Development
| UX/UI wireframe design |  | 2025-08-07 | 2025-08-16 | TD | bar: T to F; M; W to F
| Main Page + Menu Navigation |  | 2025-08-17 | 2025-08-23 | WK | bar: M to F
| Login / Register Page |  | 2025-08-24 | 2025-08-31 | TD | bar: M to F
| Charger Page |  | 2025-09-01 | 2025-09-06 | WK | bar: M to F
| MDB Iot Page |  | 2025-09-07 | 2025-09-13 | TD , WK | bar: M to F
| Maintenance report page |  | 2025-09-14 | 2025-09-20 | TD | bar: M to F
| Test report page |  | 2025-09-21 | 2025-10-01 | TD | bar: M to F; M to W
| Predictive Maintenance page |  | 2025-10-02 | 2025-10-10 | TD | bar: T to F; M to F
| Health Index Page |  | 2025-10-11 | 2025-10-18 | TD | bar: T to F
| Setting Page |  | 2025-10-19 | 2025-10-25 | TD | bar: M to W; F
Backend API + DB Integration (12.2.1)
| Create Data Base |  | 2025-08-07 | 2025-08-11 | TS |  |  | 2025-09-06 | bar: T to F; M
| Connect MongoDB/PostgreSQL |  | 2025-08-12 | 2025-08-16 | TS | bar: W to F
| Auth API |  | 2025-08-17 | 2025-08-23 | TS | bar: M to F
| Station Info API |  | 2025-08-24 | 2025-08-31 | TS , WK | bar: M to F
| Setup MQTT/WS for real-time | 2025-09-01 | 2025-09-01 | 2025-09-06 | TS , WK | bar: M to F
Predictive AI Module Integration (12.2.3)
| File Upload/Download |  | 2025-09-07 | 2025-09-13 | TS | bar: M to F
| Upload/Download system of Test & PM Report |  | 2025-09-14 | 2025-09-20 | TS | bar: M to F
| Setup REST API for 7 AI Modules |  | 2025-09-21 | 2025-10-01 | VA | bar: M to F; M to W
| Design Prediction Input/Output UI |  | 2025-10-02 | 2025-10-10 | VA | bar: T to F; M to F
| Telegram/Email Notification Setting |  | 2025-10-11 | 2025-10-25 | TS | bar: T to F; M to W; F
Final Test
| Connect API , End to End test , Debug & Optimize |  | 2025-10-26 | 2025-11-05 | ALL | bar: M to F; M to W
3 | System Testing, UI Refinement, and Deployment | bar: T to F
| Internal Testing (Unit & Integration) |  | 2025-11-06 | 2025-11-26 | ALL | bar: T to F; M to F; M to F; M to W
| System QA & Error Handling |  | 2025-11-27 | 2025-12-16 | ALL | bar: T to F; M to T; M to F; M to T
| Data Simulation & User Scenario Testing |  | 2025-12-17 | 2026-01-06 | TS , TD | bar: W to F; M to F; M to T; T to F; M to T
| User Training & User Manual & Documentation |  | 2026-01-07 | 2026-01-21 | ALL | bar: W to F; M to F; M to W
| UAT |  | 2026-01-22 | 2026-02-11 | ALL | bar: T to F; M to F; M to F; M to W
| Feedback |  | 2026-02-12 | 2026-02-21 | ALL | bar: T to F; M to F
| System Handover & Final Delivery |  | 2026-02-22 | 2026-03-05 | ALL | bar: M to F; M to T

## Holiday2024 (hidden)
Holiday Name | Holiday Date
วันขึ้นปีใหม่ | 2024-01-01
วันหยุดชดเชยวันส่งท้ายปี | 2024-01-02
วันหยุดชดเชยวันมาฆบูชา | 2024-02-26
วันหยุดชดเชยวันจักรี | 2024-04-08
วันสงกรานต์ | 2024-04-15
วันหยุดชดเชยวันสงกรานต์ | 2024-04-16
วันแรงงานแห่งชาติ | 2024-05-01
วันหยุดชดเชยวันฉัตรมงคล | 2024-05-06
วันวิสาขบูชา | 2024-05-22
วันเฉลิมพระชนมพรรษาสมเด็จพระนางเจ้าฯ พระบรมราชินี | 2024-06-03
วันหยุดชดเชยวันอาสาฬหบูชา | 2024-07-22
วันหยุดชดเชยวันเฉลิมพระชนมพรรษาพระบาทสมเด็จพระวชิรเกล้าเจ้าอยู่หัว รัชกาลที่ 10 | 2024-07-29
วันแม่แห่งชาติ วันเฉลิมพระชนมพรรษา สมเด็จพระนางเจ้าสิริกิติ์ พระบรมราชินีนาถ พระบรมราชชนนีพันปีหลวง | 2024-08-12
วันหยุดชดเชย วันคล้ายวันสวรรคต พระบาทสมเด็จพระบรมชนกาธิเบศร มหาภูมิพลอดุลยเดชมหาราช บรมนาถบพิตร | 2024-10-14
วันปิยมหาราช | 2024-10-23
วันพ่อแห่งชาติ | 2024-12-05
วันรัฐธรรมนูญ | 2024-12-10
วันสิ้นปี | 2024-12-31
วันขึ้นปีใหม่ | 2025-01-01
วันมาฆบูชา | 2025-02-12
วันหยุดชดเชยวันจักรี | 2025-04-07
วันสงกรานต์ | 2025-04-14
วันสงกรานต์ | 2025-04-15
วันหยุดชดเชยวันสงกรานต์ | 2025-04-16
วันแรงงานแห่งชาติ | 2025-05-01
วันหยุดชดเชยวันฉัตรมงคล | 2025-05-05
วันหยุดชดเชยวันวิสาขบูชา | 2025-05-12
วันเฉลิมพระชนมพรรษาสมเด็จพระนางเจ้าฯ พระบรมราชินี | 2025-06-03
วันอาสาฬหบูชา | 2025-07-10
วันเข้าพรรษา | 2025-07-11
วันเฉลิมพระชนมพรรษาพระบาทสมเด็จพระวชิรเกล้าเจ้าอยู่หัว รัชกาลที่ 10 | 2025-07-28
วันแม่แห่งชาติ วันเฉลิมพระชนมพรรษา สมเด็จพระนางเจ้าสิริกิติ์ พระบรมราชินีนาถ พระบรมราชชนนีพันปีหลวง | 2025-08-12
วันคล้ายวันสวรรคต พระบาทสมเด็จพระบรมชนกาธิเบศร มหาภูมิพลอดุลยเดชมหาราช บรมนาถบพิตร | 2025-10-13
วันปิยมหาราช | 2025-10-23
วันพ่อแห่งชาติ | 2025-12-05
วันรัฐธรรมนูญ | 2025-12-10
วันสิ้นปี | 2025-12-31